# Status Report 1

# 22 June 2004

Executive summary

  - Detailed implementation plans of all Work Packages have been established and launched.

  - All collaborators have started their activities.

  - Andries den Ouden (TEU) has set up a NED wep page:

http://lt.tnw.utwente.nl/project.php?projectid=9

  - CIEMAT, in Spain, has expressed interest in joining the NED collaboration and has offered to contribute 18 staff.month of manpower to carry out magnet design computation.

  - CIEMAT contribution + additional resources available at CEA and CERN enable the re-enactment of some of the Tasks of the Magnet Design and Optimization Working Package that was included in the initial CARE proposal; this re-enactment will be carried out by the means of an informal Working Group.

  - Proposition will be made to the July NED Steering Committee meeting to modify the scope of work of the sub-Task on innovative insulation (4.4) to better suit the Activity needs and to match its schedule with that of the sub-Task on conventional insulation (4.3).  The proposed modifications are

    - To change the title of sub-Task 4.4.2 from “Pre-impregnation/wrapping bench” to  “Characterization tests,”

    - To extend the scope of the report on conventional insulation programme due on 31 July 2004 (task 4.3) to include the programme on innovative insulation,

    - To extend the sub-task duration until 28 December 2005 and to delay the delivery of the report on innovative insulation (initially due on 30 June 2005) until this date.

  - INFN/Genova has offered to extend its contribution to NED and to re-instate the sub-Task (included in the initial CARE proposal) on mechanical modelling of multifilament composite wires to simulate cabling effects.

  - A 1-year job opportunity to work on quench computation (Task 2.3) has been advertised at INFN/Milano-LASA.

WP1: Management and Communication (M&C)

  - Activity coordination

- 19–21 November 2003: participation of A. Devred (CEA) and A. den Ouden (TEU) to CARE Kick Off meeting at CERN

- 13 January 2004: visit of A. Devred (CEA) to INFN/Genova

- 16 January 2004: visit of A. Devred and P. Védrine (CEA) to CIEMAT

- 27 January 2004: visit of A. Devred (CEA) to TEU

- 13 February 2004: A. Devred (CEA), P. Lebrun and L. Rossi (CERN) to INFN/Milano-LASA

- 23–24 February 2004: participation of A. Devred (CEA) to 1st CARE Steering Committee and Dissemination Board meetings in Paris, France

- 19 March 2004: visit of A. Devred, F. Rondeaux and P. Védrine (CEA) to RAL

- 22–24 March 2004: participation to Workshop on Accelerator Magnets Superconductor (WAMS) organized within the framework of AMT Work Package of HEHIHB Network Activitiy

- 13 April 2004: visit of A. Devred (CEA) and M. Pojer (CERN) to INFN/Genova

- 2–3 June 2004: visit of A. Devred, B. Baudouy and F. Michel (CEA), and R. Van Weelderen (CERN) to WUT

- 24–25 June 2004: participation of A. Devred (CEA) and A. den Ouden (TEU) to 2nd CARE Steering Committee and Dissemination Board meetings in Warsaw, Poland

WP1: Management and Communication (M&C; Cont.)

1.2 Meetings

1.2.1. Steering Committee (SC) Meetings

- 8 January 2004: first meeting at CERN

- A. Devred (CEA), D. Leroy, L. Rossi and H. ten Kate (CERN), P. Fabbricatore (INFN/Genova), G. Volpini (INFN/Milano), E. Baynham (RAL), and A. den Ouden (TEU)

- 25 March 2004; second meeting at CERN

- B. Baudouy, A. Devred and J.M. Rifflet (CEA), D. Leroy (CERN), F. Toral (CIEMAT), G. Volpini (INFN/Milano), E. Baynham and S. Canfer (RAL), and A. den Ouden (TEU) + A. Yamamoto (KEK), S. Gourlay (LBNL)

- 8 July 2004: next meeting at CERN

1.2.2. External Scientific Advisory Committee (ESAC) Meetings

- 24 March 2004: first meeting at CERN

- 29 April 2004: publication of first ESAC report

WP1: Management and Communication (M&C; End)

1.3 Dissemination

1.3.1 Papers

- “High field accelerator magnets beyond LHC,” A. Devred, Proceedings of 2003 IEEE Particle Accelerator Conference, IEEE catalogue 03CH37423, pp. 146–150, 2003 (invited).

- “High field accelerator magnet R&D in Europe,” A. Devred, D.E. Baynham, L. Bottura, M. Chorowski, P. Fabbricatore, D. Leroy, A. den Ouden, J. M. Rifflet, L. Rossi, O. Vincent-Viry, and G. Volpini, to appear in the Proceedings of the 18th International Conference on Magnet Technology, Morioka, Japan, October 20–24, 2003 (invited).

- “Status of the Next European Dipole (NED) Activity of the Collaborated Accelerator Research in Europe (CARE) Project”, A. Devred, D.E. Baynham, M. Chorowski, P. Fabbricatore, L. Garcia-Tabares, D. Leroy, A. den Ouden, J.M. Rifflet and G. Volpini, to be presented at the Applied Superconductivity Conference, Jacksonville, FL, October 3–8, 2004 (invited).

1.3.2 Talks

- “NED Status Report,” A. Devred and T. Taylor, on behalf of the NED Collaboration, KEK, Tsukuba, Japan, 9 March 2004.

- “Next European Dipole (NED) Overview,” A. Devred, on behalf of the NED Collaboration, Journées de l’Association Française de Froid, Belfort, France, 25 May 2004.

- “Next European Dipole (NED) Overview,” A. Devred, on Behalf of the NED Collaboration, Department Of Energy (DOE), Washington, DC, 16 June 2004.

WP2: Thermal Studies and Quench Protection (TSQP)

2.1 TSQP coordination

2.2 Heat Transfer Measurements

2.2.1 Specifications' drafting

- 28 January 2004: preparatory meeting at CEA

- B. Baudouy, P. Chesny, A. Devred, B. Hervieu, F. Michel and J.M. Rifflet (CEA)

- 27 February 2004: programme proposal issued by B. Baudouy (CEA)

- March 2004: review of programme proposal by P. Lebrun and D. Leroy (CERN) and approbation by SC meeting

- 4 May 2004: cryostat specification issued by B. Baudouy, B. Hervieu and F. Michel (CEA)

- May 2004: specification submitted for review to P. Lebrun and R. Van Weelderen (CERN) and M. Chorowski (WUT)

- 8 June 2004: revised cryostat specification issued by B. Baudouy, B. Hervieu and F. Michel (CEA)

Sub-task near completion

2.2.2 Cryostat design and manufacturing

- 3 June 2004: preparatory visit to Kryosystem

- B. Baudouy, A. Devred and F. Michel (CEA), R. van Weelderen (CERN), M. Chorowski, J. Fydrych and J. Polinski (WUT), B. Adamowicz, G. Michalski and G. Strychalski (Kryosystem)

  - End of June 2004: call for tender

  - End of July 2004; contract’s handout

  - 30 September 2004: Production Readiness Review

  - End of December 2004: completion of manufacturing

  - Early January 2005: reception test at WUT

  - End of January 2005: shipment to CEA/Saclay

2.2.3 Heat exchanger module fabrication

  - 25 June 2004: preliminary design to be issued by F. Michel (CEA)

  - End of December 2004: completion of manufacturing

2.2.4 Facility integration/commissioning

  - 1 April 2004: report on commissioning (CEA & WUT); EU deliverable

2.2.5 Measurements and data analysis

  - 30 December 2005: interim report; EU milestone

  - 29 December 2006: final report (CEA); EU deliverable

WP2: Thermal Studies and Quench Protection (TSQP; Cont.)

2.3 Quench Protection Computation

- 5 March 2004: draft computation programme issued by M. Sorbi and G. Volpini (INFN/Milano-LASA)

- March 2004 SC meeting: discussion of computation programme

- June 2004: computation to be started on baseline magnetic configuration

  - 31 December 2004: interim report (INFN/Milano-LASA); EU milestone

  - 30 June 2005: final report (INFN/Milano-LASA); EU deliverable

WP3: Conductor Development (CD)

3.1 CD coordination

3.2 Preliminary design of 15 T dipole magnet

- September 2003–present: preliminary design computations carried out by O. Vincent-Viry (CERN) under D. Leroy supervision (CERN)

- January 2004 SC meeting: first presentation of preliminary design computations by O. Vincent-Viry (CERN)

- 4 May 2004: meeting at CEA to review magnetic configurations and choice of a baseline for 88 mm aperture

- A. Devred, H. Félice, L. Quettier, J.M. Riflet, P. Védrine (CEA), and D. Leroy and O. Vincent-Viry (CERN)

- 15 July 2004: interim report extended to 130 and 160 mm apertures (CERN)

  - 31 December 2004: final report (CERN); EU deliverable

3.3 Wire and cable specifications' drafting

- 11 May 2004: first draft specification issued by D. Leroy (CERN) and communicated to A. Devred (CEA)

- 14 May 2004: first draft reviewed by A. Devred (CEA)

- 18 May 2004: second draft specification issued by D. Leroy and communicated to A. Devred (CEA) and A. den Ouden (TEU)

- 1 June 2004: third draft specification issued by D. Leroy and communicated to NED SC

- 4 June 2004: Specification Committee Meeting at CERN

- T. Boutboul, P. Bryant (Chairman), P. Lebrun, D. Leroy, L. Oberli, L. Rossi and H. ten Kate (CERN)

- 18 June 2004: final specification issued by D. Leroy

  - 30 June 2004: report on specification to be issued by D. Leroy (CERN); EU deliverable

## Sub-Task near completion

3.4 Wire development and manufacturing

- 12 December 2003: preparatory visit to Alstom/MSA A. Devred (CEA), and D. Leroy, T. Boutboul and L. Oberli (CERN)

- 15 December 2003: preparatory visit to EAS

- A. Devred (CEA), D. Leroy and L. Oberli (CERN) + SMI representative

- 27 January 2004: preparatory visit to SMI

- A. Devred (CEA), D. Leroy, T. Boutboul, L. Oberli and A. Unervick (CERN) + EAS representatives

- 23 June 2004: call for tender to be sent to Alstom/MSA, EAS, OK Cu, OK SI, SMI

- Late July 2004: contracts’ signature (depending on call for tender outcome)

  - 30 June 2005: first results on wire development; EU milestone

  - 30 June 2006: final wire production; EU deliverable

WP3: Conductor Development (CD; Cont.)

3.5 Wire Characterization

3.5.1 Task coordination

- March 2004: setting up of Working Group on Wire Characterization, chaired by A. den Ouden (Twente University)

- 19 May 2004: first Working Group meeting at CERN

- L. Quettier (CEA), V. Previtali (CERN), P. Fabbricatore and M. Greco (INFN/Genova), D. Pedrini and G. Volpini (INFN/Milano), and A. den Ouden (Twente University)

- 22 September 2004: second Working Group meeting at CERN

  - 30 December 2005: interim report on wire characterization; EU milestone

  - 30 June 2006: final report on wire characterization; EU deliverable

3.5.1 Critical current measurements at CEA

3.5.2 Critical current measurements at INFN/Milano-LASA

3.5.3 Critical current measurements at Twente University

3.5.4 Magnetization measurements at INFN/Genova

- 21 January 2004: preparatory meeting at CERN

- A. Devred (CEA), D. Leroy (CERN) and P. Fabbricatore (INFN/Genova

- 23 March 2004: first report on preliminary measurements issued by P. Fabbricatore and M. Greco (INFN/Genova)

- 23 March 2004–13 April 2004: review of preliminary measurements by A. Devred (CEA) and D. Leroy (CERN)

3.6 Cable development and manufacturing

  - 31 December 2006: final cable production; EU deliverable

3.7 Cable Characterization

  - 31 December 2006: final report on cable characterization; EU deliverable

WP3: Conductor Development (CD; End)

CD Work Package Extension: 3.8 Mechanical Studies

- 28 January 2004: parameters of mechanical model for 19-subelement, internal tin wire issued by A. Devred (CEA)

- 30 January 2004: mesh proposal issued by S. Farinon (INFN/Genova)

- Early February 2004: review of mesh proposal by A. Devred (CEA), D. Leroy (CERN) and C. Verwaerde (Alstom/MSA)

- February 2004–present: review of material properties

- 25 March 2004: informal discussion of preliminary computation results

- A. Devred (CEA), D. Leroy (CERN), S. Farinon (INFN/Genova), C. Verwaerde and P. Mocaer (Alstom/MSA)

- 9 June 2004: meeting at CERN to review material properties and discuss computation results

- A. Devred (CEA), T. Boutboul, P. Fessia, D. Leroy and S. Sgobba (CERN), S. Farinon and R. Musenich (INFN/Genova), and P. Loverage (RAL)

- 7 July 2004: next meeting at CERN to review material properties and discuss computation results

WP4: Insulation Development and Implementation (IDI)

4.1 IDI Coordination

4.2 Specifications' Drafting

- 6 May 2004: version 1 of specifications issued by S. Canfer (RAL)

- 11 May 2004: conference call on insulation specifications A. Devred and F. Rondeaux (CEA), S. Canfer and J. Greenhalgh (RAL), and A. den Ouden (Twente University)

- 11 May 2004: Version 2 of specifications issued by S. Canfer (RAL)

- 25 May 2004: Version 2.2 of specifications issued by S. Canfer (RAL)

- 23 June 2004: Version 2.3 of specifications issued by S. Canfer (RAL)

  - 30 June 2004: report on specifications; EU milestone

Sub-Task near completion

4.3 Conventional Insulation

  - 31 July 2004: definition of conventional insulation programme; EU milestone

  - 28 December 2005: final report on conventional insulation; EU deliverable

4.4 Innovative Insulation

- 6 May 2004: preparatory meeting at CEA

- A. Devred, J.M. Rifflet, F. Rondeaux and P. Védrine (CEA)

  - 30 June 2005: final report on innovative insulation; EU deliverable (to be delayed until 28 December 2005)

Activity Extension: Working Group on Magnet Design and Optimization (MDO)

- April 2004: setting up of Working Group on Magnet Design and Optimization, chaired by P. Védrine (CEA), helped by F. Toral (Technical Secretary, CIEMAT)

- 19 May 2004: brainstorming session at CEA

- A. Devred, H. Felice, L. Quettier and P. Védrine (CEA), P. Fessia (CERN), S. Sanz and F. Toral (CIEMAT), and P. Loveridge and J. Rochford (RAL)

  - 31 December 2004: review of 2-D magnetic configurations; milestone

  - 30 June 2005: review of 2-D mechanical configurations; milestone

  - 28 December 2005: review of 3-D configurations; milestone