CARE/JRA2: 2nd Quarterly Report 2004

Version 20/07/2004

Title: Charge production with Photo-injectors

PHIN 	Coordinator: A. Ghigo (INFN-LNF)

Deputy: L. Rinolfi (CERN)

Participating Laboratories and Institutes:

| Institute | Acronym | Country | Coordinator | PHIN Scientific Contact | Associated to |
| --- | --- | --- | --- | --- | --- |
| CCLRC Rutherford Appleton Lab. (20) | CCLRC-RAL | UK | P. Norton | G. Hirst |  |
| CERN Geneva (17) | CERN | CH | G. Guignard | G. Suberlucq |  |
| CNRS-IN2P3 Orsay (3) | CNRS-Orsay | F | T. Garvey | G. Bienvenu | CNRS |
| CNRS Lab. Optique Appl. Palaiseau (3) | CNRS-LOA | F | T. Garvey | V. Malka | CNRS |
| ForschungsZentrum ELBE (9) | FZR-ELBE | D | J. Teichert | J. Teichert |  |
| INFN-Lab. Nazionali di Frascati (10) | INFN-LNF | I | S. Guiducci | A. Ghigo | INFN |
| INFN- Milan (10) | INFN-MI | I | C. Pagani | I. Boscolo | INFN |
| Twente University- Enschede (12) | TEU | NL | J.W.J. Verschuur | J.W.J. Verschuur |  |

###### Main Objectives: Perform Research and Development on charge-production by interaction of laser pulse with material within RF field and improve or extend the existing infrastructures in order to fulfil the objectives. Coordinate the efforts done at various Institutes on photo-injectors.

Cost:

| Total Cost | Requested Cost |
| --- | --- |
| 3.851 M€(FC) + 2.150 M€(AC) Total = 6.001 M€ | 3.542 M€ |

- Management Activity

  - Meetings:

The first PHIN Steering Committee (SC) meeting was organized in Paris on 3rd February  2004.

The second PHIN SC meeting was organized in Frascati on 6th May  2004 in parallel with the ELAN SC meeting.

The next SC meeting is foreseen in Hamburg on November in parallel with the CARE general meeting.

PHIN responsible participated to the Meeting of the CARE Steering Committee in Warsaw University of Technology on 24th June 2004.

A meeting took place at CERN on 18th June 2004, between DAPNIA, LAPP and CERN where PHIN issues were discussed.

A video conference was held on 14th July between CERN and RAL where progresses on Laser issues were analyzed.

1.1.1 List of meetings

1st PHIN Collaboration Meeting   2004/05/05 Frascati

2nd PHIN Steering Committee Meeting 2004/05/06 Frascati

1st ELAN Meeting 2004/05/04-06 Frascati

CERN/RAL Videoconference 2004/05/26

DAPNIA/LAPP/CERN Meeting  2004/06/18 CERN

CARE Steering Committee Meeting	2004/06/24 Warsaw

CERN/RAL Videoconference 2004/07/14

1.2.1 General meetings

1st PHIN Collaboration Meeting   05/05/04 Frascati

| Table 1.1.1a: Overview of meeting, workshop and event (co)organized by the Activity or with Activity contributions NA/JRA Activity | January | February | March | April | May | June | July |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity yearly and/ or steering meeting |  | 3 Feb. |  |  | 6 May |  |  |
| Meeting WP1 |  |  |  |  |  | 18 June Workshop DAPNIA/LAPP/CERN |  |
| Meeting WP2 |  |  |  |  |  |  |  |
| Meeting WP3 |  |  |  |  | 26 May Video Conf |  | 14 July Video Conf |
| Meeting WP4 |  |  |  |  |  |  |  |
| Joint meeting /workshop with other CARE activity |  |  |  |  | 5 May ELAN |  |  |
| Joint meeting with other collaborations |  |  |  |  |  |  |  |
| Conferences & workshops with activity contrib. |  |  |  |  |  |  |  |
| EPAC'04 |  |  |  |  |  |  | 5 - 9 Lucerne |
| CTF3 Collaboration meeting |  |  |  |  |  |  |  |

Table 1.1.1b: List of meeting, workshop and event (co)organized by the Activity

| Date | Title/subject | location | Main organizer | Number of participants | Comments and Web site |
| --- | --- | --- | --- | --- | --- |
| 04 06 05 | 1st PHIN Collaboration Meeting | Frascati | LNF | 25 |  |
| 04 05 05 | 2nd PHIN Steering Committee | Frascati | LNF | 5 |  |
| 04 05 4-6 | 1st ELAN Meeting | Frascati | LNF | 90 |  |
| 04 05 26 | CERN/RAL Meeting | Videoconference |  |  |  |
| 04 06 18 | DAPPNIA/LAPP/CERN Meeting | Geneva | CERN |  |  |
| 04 06 24 | CARE Steering Committee | Warsaw |  |  |  |
| 04 07 14 | CERN/RAL Meeting | Videoconference |  |  |  |

  - External Scientific Advisory Committee

    - Composition

Roberto Corsini, CERN

Klaus Floettmann, DESY

Paolo Michelato, INFN Milano - LASA

Ingo Will, Max Born Institute Berlin

    - Report of the ESAC

(Comments to the presentations given at the first PHIN meeting on May 5th, 2004 in Frascati)

The general impression of the committee is that the tasks have started according to the project planning and that no major problems have been identified at the moment. The division of the total budget seems to be appropriate for the aims to be achieved.

The committee would like to receive in advance a tentative schedule for the next meeting.

The committee would give the following comments based on the talks presented at the first PHIN cooperation meeting:

1) CERN

The project is in a good shape and is proceeding according to the schedule.

Suggestion: It would be useful to have the data on photocathode production, performance and operation in the gun well organized in a database and accessible to other institutes.

2) FZR

The project is in a good shape and is proceeding according to schedule.

3) Twente U.

Suggestion: The diagnostics in the photocathode preparation chamber should be improved, in order to ameliorate cathode performances (lifetime). It would be useful to have the data on photocathode production, performance and operation in the gun well organized in a database and accessible to other institutes.

4) RAL

We agree with the general scheme of the laser.

Suggestions:

Utilizing the energy stored in the laser rods during the total pump-up phase in more efficient way would probably allow to reduce the required amount of diodes and therefore the total costs of the laser system. It would also solve the problems with fracture limit of the laser rods. This option should be taken into account because it is of large interest for other institutions.

It may worthwhile to consider an oscillator running in burst-mode instead of CW mode.

5) LOA

The parameter space accessible with plasma acceleration seems not to match high energy physics requirements at present. More information exchange between plasma and accelerator physics communities will be useful. The laser expertise and hardware existing at LOA can be useful to other members of the collaboration.

6) LAL-Orsay

It should be clarified if a complete symmetrization of the field in the gun is necessary for CTF3 gun. In case, a coaxial coupler solution should be also considered.

7) INFN-Milano & Frascati

Both groups have presented different techniques to solve the same aim to produce flat-top pulses. We suggest joining the activities of both groups and use the short-pulse laser at Politecnico Milano as a test bench for the different pulse shapers under development.

2. Dissemination Activity

2.1 List of talks

Charge Production with Photo-injectors

Andrea Ghigo (INFN-LNF)

1st ELAN Meeting, Frascati

2004/5/4

## ELAN - PHIN JRA Connection

Andrea Ghigo (INFN-LNF)

1st ELAN Meeting, Frascati

2004/5/4

## CERN Activities within the PHIN framework until April 04

Guy Suberlucq (CERN)

1st ELAN Meeting, Frascati

2004/5/4

Overview of the present status of the SRF gun design and construction,

J. Teichert  (FZR)

1st ELAN Meeting, Frascati 2004/5/4

also presented at the PHIN Collaboration Meeting

also CARE-Note-2004-010-ELAN

## Laser Pulse Manipulation; first experience with Dazzler

Carlo Vicario (INFN-LNF)

1st ELAN Meeting, Frascati

2004/5/4

## Considerations on a Laser pulse shaping for a RF - gun

Simone Cialdi (INFN-MI)

1st ELAN Meeting, Frascati

2004/5/4

## Photo-injector laser development

Marta Divall (CLF)

1st ELAN Meeting, Frascati

2004/5/4

## Status Report from JRA2 “PHIN”

L. Rinolfi / CERN CARE Meeting 2004/6/23

## Photoinjector Lasers for 4GLS and CERN

Graeme Hirst (CCLRC-RAL)

Internal seminar, RAL

2004/06/07

## Technology Challenges for High  Brightness Photo-injectors

Guy Suberlucq (CERN)

EPAC 2004, Lucerne, 2004/7/6

  - List of talks

Table 2.1: List of talks to workshops and conferences made by NA/JRA members and which are about (or include) activities carried within your NA or JRA

| # | Subject | Speaker/Lab | Event | Date | Talk Web site | CARE-Conf |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Overview of the present status of the SRF gun design and construction | J. Teichert /FZR | PHIN Collaboration Meeting | 04/05/04 | http://www.infn.it/phin/PHIN_Coll_Meeting-2004-05-05.html |  |
| 2 | ELAN - PHIN JRA Connection | A. Ghigo/INFN | PHIN Collaboration Meeting | 04/05/04 | http://www.infn.it/phin/PHIN_Coll_Meeting-2004-05-05.html |  |
| 3 | Charge Production with Photo-injectors | A. Ghigo/INFN | PHIN Collaboration Meeting | 04/05/04 | http://www.infn.it/phin/PHIN_Coll_Meeting-2004-05-05.html |  |
| 4 | CERN Activities within the PHIN framework until April 04 | G. Suberlucq/CERN | PHIN Collaboration Meeting | 04/05/04 | http://www.infn.it/phin/PHIN_Coll_Meeting-2004-05-05.html |  |
| 5 | Laser Pulse Manipulation; first experience with Dazzler | C. Vicario/INFN | PHIN Collaboration Meeting | 04/05/04 | http://www.infn.it/phin/PHIN_Coll_Meeting-2004-05-05.html |  |
| 6 | Considerations on a Laser pulse shaping for a RF - gun | S. Cialdi/INFN | PHIN Collaboration Meeting | 04/05/04 | http://www.infn.it/phin/PHIN_Coll_Meeting-2004-05-05.html |  |
| 7 | Photo-injector laser development | M. Divall/CLF | PHIN Collaboration Meeting | 04/05/04 | http://www.infn.it/phin/PHIN_Coll_Meeting-2004-05-05.html |  |
| 8 | Photoinjector Lasers for 4GLS and CERN | Graeme Hirst /CCLRC-RAL | Internal seminar | 2004/6/7 |  |  |
| 9 | Technology Challenges for High Brightness Photo-injectors | G. Suberlucq/CERN | EPAC 2004 | 2004/7/6 | http://www/epac04.ch/ |  |
| 10 | Status Report from JRA2 “PHIN” | L. Rinolfi / CERN | CARE Meeting | 2004/ 23/6 | http://esgard.lal.in2p3.fr/Project/Activities/Current/CAREmeetings/Warsaw/ |  |

  - List of papers

ID: 477 - TUYBCH02  Technological Challenges for High Brightness Photo-injectors Guy Suberlucq (CERN, Geneva) Speaker   Guy Suberlucq (CERN, Geneva), Invited Oral Presentation  EPAC 2004 Lucerne

ID: 1143 - TUPLT063  Laser Temporal Pulse Shaping Experiment For SPARC Photoinjector Authors   Carlo Vicario, Andrea Ghigo (INFN/LNF, Frascati (Roma)), Simone Cialdi, Alessandro Federico Flacco (INFN-Milano, Milano), Massimo Petrarca (INFN-Roma, Roma), Mauro Nisoli, Giuseppe Sansone, Salvatore Stagira (Politecnico/Milano, Milano), Ilario Boscolo, Caterina Vozzi (Universita' degli Studi di Milano, MILANO) Presenter   Carlo Vicario (INFN/LNF, Frascati (Roma)), Type of Presentation   Poster

ID: 765 - MOPKF015  A Superconducting Photo-Injector with 3+1/2- Cell Cavity for the ELBE Linac Authors   Jochen Teichert, Hartmut Buettig, Pavel Evtushenko, Dietmar Janssen, W.-D. Lehmann, Ulf Lehnert, Peter Michel, Christof Schneider, Juergen Stephan (FZR, Dresden), Vladimir Volkov (BINP SB RAS, Novosibirsk), Ingo Will (MBI, Berlin) Presenter   Jochen Teichert (FZR, Dresden), Type of Presentation   Poster

Features of a phase-only shaper relative to a long rectangular ultraviolet pulse, S. Cialdi, I. Boscolo and A. Flacco, J. Opt. Soc. Am. {\bf 21}, (2004) 1693.

A laser pulse shaper for the low emittance radiofrequency SPARC electron gun, S. Cialdi, I. Boscolo, Nucl. Insrtrum. Meth.  Phys. Res. A {\bf 526} (2004) 239-248.

Overview of the present status of the SRF gun design and construction ,J. Teichert, P. Evtushenko, D. Janssen, W.-D. Lehmann, U. Lehnert, P. Michel, Ch. Schneider, J. Stephan, V. Volkov, I. Will, FZR,  May 2004 CARE-Note-2004-010-ELAN

#### Report on Photocathodes, J. Teichert, R. Xiang, G. Suberlucq, J.W.J. Verschuur, PHIN Internal Report.

PHIN report GUN:  First Orsay Status Report for JRA2 (PHIN) of the CARE Project LAL-Orsay staff

Table 2.2: List of document related with PHIN JRA

| # | CARE document type and number | Title | Authors and Labs | Date |
| --- | --- | --- | --- | --- |
| 1 | EPAC04 TUYBCH02 | Technological Challenges for High Brightness Photo-injectors | G. Suberlucq (CERN) |  |
| 2 | EPAC04 TUPLT063 | Laser Temporal Pulse Shaping Experiment For SPARC Photoinjector | Carlo Vicario, Andrea Ghigo (INFN/LNF, Frascati), Simone Cialdi, Alessandro Federico Flacco (INFN-Milano), Massimo Petrarca (INFN-Roma), Mauro Nisoli, Giuseppe Sansone, Salvatore Stagira (Politecnico/Milano), Ilario Boscolo, Caterina Vozzi (Universita' degli Studi di Milano) |  |
| 3 | EPAC04 MOPKF015 | A Superconducting Photo-Injector with 3+1/2- Cell Cavity for the ELBE Linac | Jochen Teichert, Hartmut Buettig, Pavel Evtushenko, Dietmar Janssen, W.-D. Lehmann, Ulf Lehnert, Peter Michel, Christof Schneider, Juergen Stephan (FZR, Dresden), Vladimir Volkov (BINP SB RAS, Novosibirsk), Ingo Will (MBI, Berlin) |  |
| 4 | CARE-Note-2004-010-ELAN | Overview of the present status of the SRF gun design and construction | J. Teichert, P. Evtushenko, D. Janssen, W.-D. Lehmann, U. Lehnert, P. Michel, Ch. Schneider, J. Stephan, V. Volkov, I. Will FZR |  |
| 5 | CARE Report | Internal report: Report on Photocathodes | J. Teichert, R. Xiang, G. Suberlucq, J.W.J. Verschuur |  |
| 6 | CARE Report | PHIN report GUN: First Orsay Status Report for JRA2 (PHIN) of the CARE Project | LAL-Orsay staff |  |
| 7 | J. Opt. Soc. Am. {\bf 21}, (2004) 1693 | Features of a phase-only shaper relative to a long rectangular ultraviolet pulse | S. Cialdi, I. Boscolo and A. Flacco |  |
| 8 | Nucl. Insrtrum. Meth. Phys. Res. A {\bf 526} (2004) 239-248 | A laser pulse shaper for the low emittance radiofrequency SPARC electron gun | S. Cialdi, I. Boscolo |  |

  - Web site

A PHIN web page has been set up at the URL

http://www.infn.it/phin/

The page shows the institutions participating to the JRA and provides links to their web sites.

General documentation such as the PHIN proposal and reports on the various activities is accessible.

The web page contains also a report on the first PHIN Collaboration Meeting, that took place in Frascati on May 5th 2004. In particular, all the presentations given at the meeting are accessible by the reader.

Every Work Package has a dedicated section which includes reports on their activities and other specific documents.

Useful excel file that includes information on a large number of semiconductor photocathodes is also available.

Te web site is continuously maintained in order to provide up-to-date information on PHIN activities.

- Additional staff hiring

The participating institutes have been used their own contracts and procedures for additional staff recruitment. The following Table shows the list of the temporary contract assigned.

Table 3: Temporary staff hiring

| # | Lab | Job Type | Duration | Work subject | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | CERN | Fellow | 18 months | Laser and photocathodes development |  |
| 2 | FZR | Post Doc | 24 months | Simulation design measurements of SFR gun | Hired on 2004/5/17 |
| 3 | FZR | Post Doc | 24 months | Photocathode preparation | Hired on 2004/7/15 |
| 4 | INFN-LNF | Post Doc | 24 months | Photo-injector diagnostic instruments | Hired on 2004/5/24 |
| 5 | CCLRC-RAL | PostDoc | 24 months | Laser development | Hired on 2004/4/01 |
| 6 | INFN-Mi | Graduated | 6 months | Electronic device development |  |

4. Status of the Work:

Work Package 2: Charge Production: CP (Leader: , J. Teichert, FRZ-ELBE)

CERN, FZR-ELBE, TEU:

The characteristics of more than 30 photocathodes, including quantum efficiency, operating laser wavelength, lifetime, vacuum conditions, etc., were collected and compared in a report (available on PHIN web page).

CERN:

The layout of the photoinjector installation in a dedicated area at CERN is completed.

The lifetime studies and measurements of the most promising photocathodes are in progress.

FZR-ELBE:

The fabrication of the parts of the new  photocathode preparation equipment is finished.

Standard vacuum components have been ordered and the assembling of the chamber will start.

The work on the report “Photocathode studies” has been continued.

CNRS-Orsay

Review of the cathode preparation chamber has been done.  Modified drawing to make easier the construction of the chamber and the cathode production is under way.

CNRS-LOA:

The spectrometer project for energy measurements of the electron beam produced in the plasma photoinjector is in progress.

Table 4.2a : Status of the WP on charge production

| WBS # | Title | Original begin date (Annex 1) | Original end date (annex1) | Estimated Status | Revised end date |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Photocathode (PC) for 3 GHz RF gun |  |  |  |  |
| 2.1.1 | High efficiency PC comparison | Jan 2004 | Dec 2005 | 60% |  |
| 2.1.2 | PC Preparation Equipment Design | Jan 2004 | Sep 2004 | 80% |  |
| 2.1.3 | PC Preparation Equipment construction | Sep 2004 | Jun 2005 | 35% |  |
| 2.1.4 | PC for 3 GHz RF high field R&D | May, 2004 | June 2005 | 0% |  |
| 2.2 | Photocathode for SC cavity |  |  |  |  |
| 2.2.1 | PC preparation equipment upgrade | Jan 2004 | Jun 2005 | 35% |  |
| 2.2.2 | PC tests | Jun 2005 | Jan 2007 | 0% |  |
| 2.3 | Laser driven plasma source |  |  |  |  |
| 2.3.1 | High energy plasma source design | Jan 2004 | Oct 2004 | 30% |  |
| 2.3.2 | 100 MeV laser plasma source R&D | Oct 2004 | Dec 2007 | 0% |  |

Table 4.2b: Status with respect to the interim reports and deliverables to be done in 2004 according to the MS project breakdown

| WBS # | Title | Due date in Annex 1 | Status | Revised delivery date |
| --- | --- | --- | --- | --- |
| 2.1.1 | High efficiency PC comparison internal report | Dec 2004 | 100% | Jun 2004 |
| 2.4.2 | Plasma source design report | Oct 2004 | 40% | Dec 2004 |

.

Work Package 3: Laser:  LAS (Leader: G. Hirst, CCLRC-RAL)

CCLRC-RAL:

Photoinjector laser design has been modified to allow operation at 50Hz, this involved re-balancing the thermal loads on the Nd:YLF amplifier rods to avoid thermal fracture. A group at the Technical University of Vienna has experience in this area and is collaborating with a Russian company who use ion-exchange techniques to improve Nd:YLF's thermal shock resistance. It was agreed with CERN to support a small research exercise in this area.

The laser oscillator call-for-tender documents were prepared by CERN and distributed. Two replies were received by the deadline in August and a final decision was deferred until after visits to the companies. Both companies tendered for an oscillator and also for a preamplifier to raise the cw power to a level suitable for injection into the pulsed amplifiers.

Investigations of possible laser diode suppliers and of the available diode technology have continued and by the end of the reporting period we were converging on a specification.

CNRS-Orsay:

The tender request of the picosecond pulsed UV laser, that is planned for NEPAL photoinjector, is under way:

Technical specifications are ready and in the hands of the administration in view of a call to tender. Four firms have been contacted.

INFN-LNF:

Second experiment on pulse shaping with the acousto-optic modulator (Dazzler) has been performed on a different configuration of the Ti:Sa laser in collaboration with Brookhaven Labs.. Also the results of this experiment are very promising and an emittance measurement of an electron beam produced in a metallic photocathode is foreseen.

INFN-MI:

Theoretical studies of temporal pulse shaping using a Liquid Crystal Mask (LCM) have been completed and the project of the 4f-system driven by a Nd:YAG has been completed and the orders for the components have been started.

The existing laser was modified and upgraded in order to perform the pulse shaping measurements using LCM: the goal of a stable operation with 90 ps has been reached; the project of the laser up-grading with the SESAM technology has been started; the first tests on the problem of the spectrum increase via self-phase modulation within an optic fiber has been done.

The study for the synchronization of the laser oscillator and the amplifier has been started.

Diagnostic tools development for the measurements is in progress.

Table 4.3a : Status of the WP on laser

| WBS # | Title | Original begin date (Annex 1) | Original end date (annex1) | Estimated Status | Revised end date |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Laser System |  |  |  |  |
| 3.1.1 | High power oscillator design | Jan 2004 | Jun 2004 | 100% |  |
| 3.1.2 | High power oscillator construction | Jun 2004 | Jan 2005 | 0% |  |
| 3.1.3 | High power amplifier design | Jan 2004 | Sep 2004 | 70% |  |
| 3.1.4 | High power amplifier construction | Sep 2004 | Jul 2005 | 0% |  |
| 3.1.5 | Oscillator+amplifier test | Aug 2005 | Dec 2005 | 0% |  |
| 3.2 | Pulse shaping (PS) |  |  |  |  |
| 3.2.1 | PS Simulation and design | Jan 2004 | Jun 2004 | 85% |  |
| 3.2.2 | Phase mask acquisition and test | Jun 2004 | Apr 2005 | 30% |  |
| 3.2.3 | Dazzler acquisition and test | Jan 2004 | May 2005 | 80% |  |
| 3.2.4 | Pulse shaping comparison | May 2005 | Oct 2005 | 0% |  |
| 3.3 | UV generation and feedbacks |  |  |  |  |
| 3.3.1 | UV harmonic generator R&D | Jan 2004 | Jun 2004 | 35% |  |
| 3.3.2 | UV harmonic generator test | Jun 2004 | Apr 2005 | 0% |  |
| 3.3.3 | Laser-RF feedback development | Jan 2004 | Jun 2005 | 20% |  |

Table 4.3b: Status with respect to the interim reports and deliverables to be done in 2004 according to the MS project breakdown

| WBS # | Title | Due date in Annex 1 | Status | Revised delivery date |
| --- | --- | --- | --- | --- |
| 3.1.1 | Oscillator Techn. Specs for tender request | Jun 2004 | 100% |  |
| 3.1.3 | Amplifier design report | Aug 2004 | 70% | Dec 2004 |
| 3.2.1 | PS Simulation and design report | Jun 2004 | 85% | Oct 2004 |
| 3.3.1 | UV harmonic generator R&D report | Jun 2004 | 35% | Dec 2004 |

Work Package 4: RF Gun and Beam Dynamics: GUN

(Leader: G.Bienvenu, CNRS-Orsay)

CNRS-Orsay:

The 3 GHz RF gun design has been completed (complete report in the PHIN web page).

As suggested by members of the last review committee, the possibility to use a coaxial coupler to feed the RF gun instead of our two ports coupler has been carefully checked with HFSS simulations.

Better field symmetry in the coupler cavity has been studied: racetrack geometry for this volume has been used to eliminate undesirable quadrupolar effects.

Vacuum pumping speed has been increased to pump not only by the axial canal but also by 44 holes distributed in the half-cavity and the second cavity and connected to an integrated coaxial NEG pump.

The final operational design is now ready to call for quotation and final mechanical drawing are under way.

FZR-ELBE:

The design of the cryomodule for the SRF gun has been completed.

The fabrication of the photocathode cooling system is finished.

A test bench (vacuum chamber with liquid nitrogen cooling system) for experimental test of the photocathode cooling system has been installed.

Table 4.3a : Status of the WP on RF gun

| WBS # | Title | Original begin date (Annex 1) | Original end date (annex1) | Estimated Status | Revised end date |
| --- | --- | --- | --- | --- | --- |
| 4.1 | SC RF gun |  |  |  |  |
| 4.1.1 | SC RF gun Technology development | Jan 2004 | Jul 2004 | 100% |  |
| 4.1.2 | SC RF gun design | Jan 2004 | Dec 2004 | 50% |  |
| 4.1.3 | SC RF gun realization | Jan 2005 | Feb 2006 | 0% |  |
| 4.1.4 | SC RF gun test | Feb 2006 | Jan 2007 | 0% |  |
| 4.2 | 3 GHz RF gun |  |  |  |  |
| 4.2.1 | 3 GHz RF gun design | Jan 2004 | Dec 2004 | 100% |  |
| 4.2.2 | Two RF gun construction | Jan 2005 | Jun 2005 | 0% |  |
| 4.2.3 | CTF3 RF gun test | Jun 2005 | Sep 2006 | 0% |  |
| 4.2.4 | NEPAL RF gun test | Jul 2005 | Feb 2007 | 0% |  |
| 4.3 | Spectrometer for e- beam |  |  |  |  |
| 4.3 | 1-50 MeV Spectrometer design | Jan 2004 | Apr 2004 | 40% |  |
| 4.3.1 | 1-50 MeV Spectrometer construction | Apr 2004 | Dec 2005 | 0% |  |
| 4.3.2 | 1-50 MeV Spectrometer test | Jan 2006 | Sep 2007 | 0% |  |
| 4.3.3 | 0 – 1 Gev Spectrometer development | Jan 2006 | Dec 2007 | 0% |  |

Table 4.3b: Status with respect to the interim reports and deliverables to be done in 2004 according to the MS project breakdown

| WBS # | Title | Due date in Annex 1 | Status | Revised delivery date |
| --- | --- | --- | --- | --- |
| 4.1.2 | SC RF gun design | Dec 2004 | 50% |  |
| 4.2.1 | 3 GHz RF gun design | Dec 2004 | 80% |  |
| 4.3.1 | 1-50 MeV Spectrometer design | Apr 2004 | 50% | Oct 2004 |